## Dashboard
HOUSE EXTENSION EXECUTIVE COST & ANALYTICS DASHBOARD
Live construction budget tracking, contractor tender commitments, and expenditure analytics
TOTAL BUDGET |  | COMMITTED QUOTES |  | TOTAL INVOICED |  | ACTUAL PAID |  | CONTINGENCY FUND | REMAINING BUDGET
146000 |  | 121700 |  | 63800 |  | 40100 |  | 12000 | 82200
Approved Baseline |  | Awarded Tenders |  | All Invoices Raised |  | Settled Cash Outflow |  | 10% Reserve Buffer | Uninvoiced Balance
Budget Consumption: |  |  |  |  | Invoiced: 43.7% of Total Budget
PHASE & TRADE BREAKDOWN SUMMARY
Construction Phase | Scope & Trades | Target Budget | Committed Quotes | Actual Paid | Status
1. Pre-Construction | Design, structural calcs & building control | 8500 | 6400 | 7600 | In Progress
2. Groundwork & Foundations | Site strip, trenching, DPM, insulated slab | 20500 | 20000 | 20000 | Complete
3. Superstructure & Envelope | Masonry cavity walls, roof, bi-folds & glazing | 43500 | 42800 | 12500 | In Progress
4. First Fix & Services | Stud partitions, rewiring, UFH & plumbing | 22500 | 21800 | 0 | Pending
5. Internal Fit-Out & Finishes | Drylining, kitchen, bathroom, flooring, decor | 35000 | 30700 | 0 | Pending
6. External Works & Paving | Patio extension, gullies & drainage | 4000 | 0 | 0 | Pending
7. Contingency Reserve | Unforeseen site variations buffer (10%) | 12000 | 0 | 0 | Available
Total Extension Tracking | All construction stages sum | 146000 | 121700 | 40100 | On Target
HOW TO RESET TO A BLANK TEMPLATE
🔄 RESET TEMPLATE Clear demo data to begin |  | 1. Clear Budget: Open 'Budget' tab and clear target values in C5:D20 →
2. Clear Quotes: Open 'Quotes Log' tab and delete demo records in A5:J24 →
3. Clear Invoices: Open 'Invoices & Payments' tab and delete rows in A5:K18 →
ℹ️ All Dashboard summary cards, phase tables, and the visual chart will automatically update to zero.
🚀 Prefer automated tracking without spreadsheets? Upgrade to CostTrack.build ↗
PROJECT AUTOMATION & COST INTELLIGENCE
CostTrack.build — Automate Your Construction Budgets & Quotes ↗
Eliminate manual spreadsheet entry. CostTrack automatically tracks quotes, manages contractor tenders, and logs invoices.
Visit costtrack.build to automate project finances, benchmark UK build rates, and protect your contingency fund.

## Budget
HOUSE EXTENSION MASTER BUDGET & CONTINGENCY TRACKER
Project Cost Benchmarking: | Automate budget calculations & trade rate benchmarks at CostTrack.build →
Category | Scope Description | Target Budget | Committed Quote | Incurred Cost | Variance | Status
Design & Planning | Architectural drawings, structural calculations, planning approval | 6500 | 6400 | 6400 | 100 | In Progress
Groundwork & Excavation | Demolition, foundation trenching, soil removal, spoil skip hire | 11000 | 10800 | 10800 | 200 | In Progress
Substructure & Foundations | Concrete footings, DPC/DPM, sub-base, insulated screed slab | 9500 | 9200 | 9200 | 300 | In Progress
Superstructure & Masonry | Cavity brickwork, external blockwork, cavity insulation, wall ties | 17500 | 17200 | 12500 | 5000 | In Progress
Roofing & Rainwater | Timber rafters, breathable membrane, slate tiles, fascias, guttering | 12500 | 12200 | 6100 | 6400 | In Progress
Glazing & External Doors | Aluminium bi-fold doors, bespoke picture window, roof lantern | 13500 | 13400 | 6700 | 6800 | In Progress
First Fix Carpentry | Stud walls, door linings, flooring joists, ceiling frameworks | 5000 | 4800 | 2400 | 2600 | In Progress
Electrical Installations | Full extension wiring, consumer board upgrade, first/second fix | 8500 | 8200 | 4100 | 4400 | In Progress
Plumbing & Heating | Underfloor heating system, radiator loops, waste & hot/cold supply | 9000 | 8800 | 4400 | 4600 | In Progress
Plastering & Drylining | Acoustic insulation, plasterboard, skimming walls and ceilings | 5500 | 5300 | 0 | 5500 | Committed
Kitchen Supply & Fit | Kitchen units, stone worktops, island installation, extractor fit | 16000 | 15800 | 0 | 16000 | Committed
Bathroom & Sanitaryware | Utility room cloaks, WC suite, plumbing fittings, vanity unit | 4500 | 4200 | 0 | 4500 | Committed
Flooring & Tiling | Subfloor leveling, engineered oak flooring, splashback tiling | 5500 | 5400 | 0 | 5500 | Committed
Painting & Decorating | Internal mist coats, vinyl matt emulsion, woodwork finish | 3500 | 0 | 0 | 3500 | Not Started
External Works & Landscaping | Patio paving tie-in, soakaway drainage, exterior step masonry | 4000 | 0 | 0 | 4000 | Not Started
Building Control & Certification | Building regulations site inspections, completion certificates | 2000 | 0 | 1200 | 800 | In Progress
Project Contingency (10%) | Buffer for structural unforeseen ground conditions & variances | 12000 | 0 | 0 | 12000 | Not Started
Total Construction Cost | Comprehensive extension budget sum | 146000 | 121700 | 63800 | 82200 | On Track

## Quotes Log
CONTRACTOR QUOTES & TENDER COMPARISON LOG
Quote Benchmarks: | Automate quote comparisons & contractor vetting at CostTrack.build →
Quote ID | Trade Category | Contractor Name | Scope Overview | Quoted Amount | Target Budget | Variance | Status | Lead Time | Notes
Q-100 | Design & Planning | Studio Architecture & Design | Full RIBA stages 1-4, engineering calcs & planning submission | 6400 | 6500 | 100 | Selected | Immediate | Planning permission approved
Q-101 | Groundwork & Excavation | Apex Civils Ltd | Site strip, 1.2m trench foundations, muck away skip transfer | 10800 | 11000 | 200 | Selected | 2 weeks | Plant hire & waste transfer notes included
Q-102 | Groundwork & Excavation | GroundWorks Direct | Foundation excavation & soil disposal | 11750 | 11000 | -750 | Declined | 3 weeks | Excludes muck away skip permits
Q-103 | Substructure & Foundations | ConcreteCore Ltd | Steel reinforced slab, DPM, insulation 100mm, screed | 9200 | 9500 | 300 | Selected | 1 week | Includes pump hire & power float finish
Q-104 | Superstructure & Masonry | Heritage Brickwork | Facing brick matching existing, dense block, lintels | 17200 | 17500 | 300 | Selected | 4 weeks | Bricks matched to original 1930s blend
Q-105 | Superstructure & Masonry | BuildRite Construction | Cavity masonry & structural steel erection | 18500 | 17500 | -1000 | Declined | 6 weeks | Higher rate due to weekend labor
Q-106 | Roofing & Rainwater | Summit Roofing Solutions | Dual-pitch rafters, Welsh slate, seamless aluminium gutters | 12200 | 12500 | 300 | Selected | 3 weeks | 25-year manufacturer guarantee on membrane
Q-107 | Glazing & External Doors | Horizon Aluminium & Glass | 4-panel Schuco bi-folds, 2.5m lantern, solar glass | 13400 | 13500 | 100 | Selected | 5 weeks | Includes survey, toughened low-E glazing & fit
Q-108 | Glazing & External Doors | ClearVision Glazing Ltd | 4-panel aluminium bi-fold system & roof lantern | 14200 | 13500 | -700 | Declined | 4 weeks | Standard U-value 1.4 W/m²K
Q-109 | First Fix Carpentry | TimberCraft Specialists | Stud partitions, door casings, ceiling battens | 4800 | 5000 | 200 | Selected | 1 week | C16 treated timber throughout
Q-110 | Electrical Installations | VoltCraft Electrical | Full first & second fix, LED circuits, NICEIC certificate | 8200 | 8500 | 300 | Selected | 2 weeks | Includes metal clad consumer unit & certification
Q-111 | Electrical Installations | SparkTech Solutions | Extension wiring & consumer board upgrade | 8900 | 8500 | -400 | Declined | 3 weeks | Does not include smart dimmers
Q-112 | Plumbing & Heating | EcoWarm Heating & Gas | Water UFH manifold, boiler tie-in, pipe runs | 8800 | 9000 | 200 | Selected | 2 weeks | Gas Safe sign-off & screed heating test
Q-113 | Plastering & Drylining | SmoothSkim Plasterers | Sound insulation, moisture boards, two-coat skim | 5300 | 5500 | 200 | Selected | 1 week | Plaster dry time allowance factored in
Q-114 | Kitchen Supply & Fit | Artisan Kitchen Studios | Shaker units, 30mm Calacatta quartz, fitting | 15800 | 16000 | 200 | Selected | 6 weeks | Includes templating & undermount sink cut-outs
Q-115 | Kitchen Supply & Fit | Bespoke Culinary Joinery | German handleless cabinetry & quartz surfaces | 17900 | 16000 | -1900 | Declined | 8 weeks | Premium imported range
Q-116 | Bathroom & Sanitaryware | AquaFlow Bathrooms | Cloakroom installation, concealed cistern, tiling prep | 4200 | 4500 | 300 | Selected | 1 week | Sanitaryware supplied by client
Q-117 | Flooring & Tiling | PrimeFloors & Stone | Acoustic underlay, engineered oak flooring throughout | 5400 | 5500 | 100 | Selected | 2 weeks | Expansion gaps & thresholds included
Q-118 | Painting & Decorating | Fineline Decorators | Sanding, undercoats, Little Greene paint finish | 3400 | 3500 | 100 | Received | 1 week | Quote under final review
Q-119 | External Works & Landscaping | Greenscape Paving | Porcelain patio extension & drainage channel | 3900 | 4000 | 100 | Received | 3 weeks | Requires sample tile approval

## Invoices & Payments
HOUSE EXTENSION INVOICE & PAYMENT MANAGEMENT LEDGER
Payment Schedule Benchmarks: | Automate stage payments & invoice management at CostTrack.build →
Invoice # | Date | Trade Category | Supplier / Contractor | Net Amount | VAT (20%) | Gross Total | Due Date | Payment Status | Payment Method | Notes
INV-001 | 2026-05-15 | Design & Planning | Studio Architecture & Design | 2666.67 | 533.33 | 3200 | 2026-05-30 | Paid | BACS Transfer | Stage 1: Measured survey & initial scheme design
INV-002 | 2026-06-20 | Design & Planning | Studio Architecture & Design | 2666.67 | 533.33 | 3200 | 2026-07-05 | Paid | BACS Transfer | Stage 2: Planning submission & structural engineering
INV-003 | 2026-07-02 | Building Control & Certification | Premier Building Control | 1000 | 200 | 1200 | 2026-07-16 | Paid | Credit Card | Initial plan check & statutory commencement notice
INV-004 | 2026-07-14 | Groundwork & Excavation | Apex Civils Ltd | 4500 | 900 | 5400 | 2026-07-28 | Paid | BACS Transfer | Stage 1: Site strip & foundation trench excavation
INV-005 | 2026-07-28 | Groundwork & Excavation | Apex Civils Ltd | 4500 | 900 | 5400 | 2026-08-11 | Paid | BACS Transfer | Stage 2: Muck away skip haulage & trench completion
INV-006 | 2026-08-08 | Substructure & Foundations | ConcreteCore Ltd | 3833.33 | 766.67 | 4600 | 2026-08-22 | Paid | BACS Transfer | Substructure stage 1: Footing concrete pour & rebar
INV-007 | 2026-08-20 | Substructure & Foundations | ConcreteCore Ltd | 3833.33 | 766.67 | 4600 | 2026-09-03 | Paid | BACS Transfer | Substructure stage 2: Oversite insulation, DPM & screed
INV-008 | 2026-09-05 | Superstructure & Masonry | Heritage Brickwork | 5416.67 | 1083.33 | 6500 | 2026-09-19 | Paid | BACS Transfer | Superstructure stage 1: Cavity brickwork to DPC level
INV-009 | 2026-09-22 | Superstructure & Masonry | Heritage Brickwork | 5000 | 1000 | 6000 | 2026-10-06 | Paid | BACS Transfer | Superstructure stage 2: Wall plate brickwork & steel beam
INV-010 | 2026-10-02 | Roofing & Rainwater | Summit Roofing Solutions | 5083.33 | 1016.67 | 6100 | 2026-10-16 | Approved | BACS Transfer | Roofing stage 1: Roof timber rafters & breathable felt
INV-011 | 2026-10-08 | Glazing & External Doors | Horizon Aluminium & Glass | 5583.33 | 1116.67 | 6700 | 2026-10-22 | Pending | BACS Transfer | 50% deposit for aluminium bi-folds & roof lantern
INV-012 | 2026-10-09 | First Fix Carpentry | TimberCraft Specialists | 2000 | 400 | 2400 | 2026-10-23 | Pending | BACS Transfer | First fix timber deliveries & internal partition frames
INV-013 | 2026-10-10 | Electrical Installations | VoltCraft Electrical | 3416.67 | 683.33 | 4100 | 2026-10-24 | Pending | BACS Transfer | First fix cabling, lighting circuits & consumer unit prep
INV-014 | 2026-10-10 | Plumbing & Heating | EcoWarm Heating & Gas | 3666.67 | 733.33 | 4400 | 2026-10-25 | Pending | BACS Transfer | First fix UFH manifold loops & boiler supply lines
Total Invoiced |  |  |  | 53166.67 | 10633.33 | 63800